## Roles and Travel
|  | Hide | Hide | Hide | Hide | Hide
INSTRUCTIONS:
Password to unlock worksheet: abc
This workbook calculates cost and schedule for a DHIS2 implementation.
BASIS OF CALCULATIONS
PEOPLE COST - HOURLY ESTIMATES | Hourly rate
Minimum is $45/hour. For per diem rate multiply by 7.5. These are blended rates. |  | Revise role names & hourly rates below; they will be automatically added to the budget summary. Remember to include a senior person as an escalation point if required.
DHIS2Expert/Researcher/Evaluator | 100 | Role 1
Project Manager/DHIS2 Implementer | 60 | Role 2
Analyst/App Developer/Tester | 45 | Role 3
Senior Escalation Point | 150 | Role 4
Researcher/Educational specialist | 80 | Role 5
*Client contribution (You can use this role to calculate your internal staff costs; it is not included in the total project budget. When you estimate hourly rates of internal staff, include costs of organizational overhead, benefits, training & supervision, divided by the average number of productive hours per day. $45/hour is equivalent to about $60,000/year salary fully loaded. but this may vary widely depending on your organization.) | 45 | Client contribution (cost of internal staff). To calculate fully-loaded labour rates see:
TRAVEL EXPENSES
See Treasury Board allowances at:
http://www.njc-cnm.gc.ca/directive/index.php?sid=98&hl=1&lang=eng
TRAVEL: Based on 2015 Treasury Board allowances for Ontario | Per unit | # of units | Total
Return airfare or train fare per person |  |  | 0
Ground transportation (57.5c/km in Ontario) |  |  | 0
Accommodation per day per person | 100 |  | 0
Meals & incidentals per day per person (Treasury Board) | 91.6 |  | 0
Event rental, setup & refreshments |  |  | 0
Printing, telecommunications, other expenses |  |  | 0
Total travel expenses |  |  | 0
This budget worksheet may be copied or adapted for nonprofit use, with attribution to LogicalOutcomes

## Budget Schedule DHIS2QuickStart
|  | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide
INSTRUCTIONS:
Blue cells & the names of activities & milestone dates are unlocked. To add tasks, copy and paste an entire row. | [12 empty] | For deliverables, enter sum of Activity start & duration into Deliv Start cell |  |  |  |  | Week Highlight: |  |  |  |  | 1
Password to unlock worksheet: abc | [7 empty] | 100 | 60 | 45 | 150 | Notes & explanations | ACTIVITY | ACTIVITY | DELIV | DELIV |  |  |  |  | Activity |  |  |  | Deliverable
|  |  | Costs for each role (hours of effort x hourly rate) |  |  |  |  | Estimated hours of effort |  |  |  |  | START | DURATION | START | DURATION | DATE | WEEKS
ACTIVITY | People cost totals | Expenses | Role 1 | Role 2 | Role 3 | Role 4 |  | Role 1 | Role 2 | Role 3 | Role 4 | Notes & explanations | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Launch project | [15 empty] | 1
Hold kick-off with team, client working group | 840 |  | 300 | 300 | 90 | 150 |  | 3 | 5 | 2 | 1 |  | 1 | 2 |  | 1 | 2015-10-01
Finalize project charter and workplan | 380 |  | 200 | 180 | 0 | 0 |  | 2 | 3 |  |  |  | 1 | 2 |  | 1
Deliverable: Project Charter | 120 |  | 0 | 120 | 0 | 0 |  |  | 2 |  |  |  |  | 1 | 2 | 1
2. Define DHIS2 requirements | [15 empty] | 1
Identify decision-makers and user groups | 380 |  | 200 | 180 | 0 | 0 |  | 2 | 3 |  |  |  | 2 | 2 |  | 1
Interview users and staff regarding M&E needs | 960 |  | 600 | 360 | 0 | 0 |  | 6 | 6 |  |  |  | 2 | 3 |  | 1
Assess business processes and existing IT system | 860 |  | 500 | 360 | 0 | 0 |  | 5 | 6 |  |  |  | 3 | 3 |  | 1
Define organizational units, user roles, datasets, reports | 985 |  | 400 | 360 | 225 | 0 |  | 4 | 6 | 5 |  |  | 4 | 3 |  | 1
Deliverable: DHIS2 Requirements Worksheet | 1310 |  | 800 | 360 | 0 | 150 |  | 8 | 6 |  | 1 |  |  | 1 | 6 | 1
3. Define program indicators | [15 empty] | 1
Review and clarify existing program indicators | 1625 |  | 800 | 600 | 225 | 0 |  | 8 | 10 | 5 |  |  | 2 | 6 |  | 1
Identify relevant indicators from external sources if applicable | 1800 |  | 600 | 1200 | 0 | 0 |  | 6 | 20 |  |  |  | 4 | 4 |  | 1
Define data elements, dissagregations, option sets | 1020 |  | 600 | 240 | 180 | 0 |  | 6 | 4 | 4 |  |  | 5 | 3 |  | 1
Validate evaluation framework with users | 760 |  | 400 | 360 | 0 | 0 |  | 4 | 6 |  |  |  | 7 | 2 |  | 1
Deliverable: List of Program Indicators and Data Elements | 490 |  | 100 | 240 | 0 | 150 |  | 1 | 4 |  | 1 |  |  | 1 | 9 | 1
4. Design reports | [15 empty] | 1
Design reports using sample data | 1650 |  | 600 | 600 | 450 | 0 |  | 6 | 10 | 10 |  |  | 5 | 3 |  | 1
Define format of import/export tables and APIs | 1305 |  | 600 | 480 | 225 | 0 |  | 6 | 8 | 5 |  |  | 5 | 4 |  | 1
Validate report designs with users | 855 |  | 300 | 420 | 135 | 0 |  | 3 | 7 | 3 |  |  | 8 | 3 |  | 1
Deliverable: DHIS2 Report Worksheet | 1250 |  | 200 | 900 | 0 | 150 |  | 2 | 15 |  | 1 |  |  | 1 | 11 | 1
5. Set up DHIS2 system | [15 empty] | 1
Configure DHIS2 instance from worksheets | 5700 |  | 3000 | 1800 | 900 | 0 |  | 30 | 30 | 20 |  |  | 12 | 3 |  | 1
Test data collection and reporting with internal users | 1680 | 500 | 300 | 480 | 900 | 0 |  | 3 | 8 | 20 |  | DHIS2 dev hosting-6 mos | 14 | 3 |  | 1
Pilot test DHIS2 system with selected users | 1470 |  | 600 | 600 | 270 | 0 |  | 6 | 10 | 6 |  |  | 17 | 5 |  | 1
Collect user feedback & incorporate changes | 1340 |  | 500 | 480 | 360 | 0 |  | 5 | 8 | 8 |  |  | 18 | 5 |  | 1
Deliverable: Beta version of DHIS2 system | 150 |  | 0 | 0 | 0 | 150 |  |  |  |  | 1 |  |  | 23 | 23 | 1
6. Transition to maintenance phase | [15 empty] | 1
Deliver training to client staff | 870 |  | 300 | 480 | 90 | 0 |  | 3 | 8 | 2 |  |  | 23 | 3 |  | 1
Transfer project to ongoing hosting and maintenance plan | 270 | 750 | 0 | 180 | 90 | 0 |  |  | 3 | 2 |  | DHIS2 production hosting-3 mos | 24 | 2
Deliverable: Working DHIS2 system | 150 |  | 0 | 0 | 0 | 150 |  |  |  |  | 1 |  |  | 26 | 26 | 1
7. Close project | [15 empty] | 1
Finalize project tasks & debrief | 325 |  | 100 | 180 | 45 | 0 |  | 1 | 3 | 1 |  |  | 27 | 1 |  | 1
Archive files including github, Zenodo | 220 |  | 100 | 120 | 0 | 0 |  | 1 | 2 |  |  |  | 27 | 2 |  | 1
Add-ons (if applicable) | [15 empty] | 1
Graphic design of reports & forms | 0 |  | 0 | 0 | 0 | 0 | [9 empty] | 1
Translation | 0 |  | 0 | 0 | 0 | 0 | [9 empty] | 1
DHIS2 app development or customization | 0 |  | 0 | 0 | 0 | 0 | [9 empty] | 1
Support of DHIS2 roll-out and implementation | 0 |  | 0 | 0 | 0 | 0 | [9 empty] | 1
Travel (see Roles and Travel worksheet) |  | 0 | 0 | 0 | 0 | 0
SUB-TOTALS | 28765 | 1250 | 12100 | 11580 | 4185 | 900 |  | 121 | 193 | 93 | 6
TOTAL COST OF PROJECT | 30015

## Interview Cost Calculator
Password to unlock worksheet: abc
Unlocked cells are blue
Time Estimator for Costing Interviews*
Provide the following information for each set of interviews:
| Time to recruit each respondent (hours) | 0
| Interview length (hours) | 0.75
| Number of interviews | 8
| Level of detail in notes: Transcript, Detailed or Summary? | Detailed
| Validation with respondent: Yes or No? | no
| Average travel time per interview (hours)* | 0
Estimated time per interview:
| Recruitment (hours)/interview | 0
| Conducting interview | 0.75
| Travel | 0
| Tidying notes (point form) | 0.75
| Validation with respondent | 0
| Total hours per interview: | 1.5
| Time for all interviews (in hours) | 12
| Time for all interviews (in days) | 1.6552
* Enter "0" travel time if interviews will be done by phone
This interview calculator may be copied and adapted for nonprofit use with attribution to Cathexis Consulting
www.cathexisconsulting.ca

## Budget Summary
| Estimated Hours | Blended Hourly Cost | Estimated Subtotal | Notes
Project Estimates |  |  |  | Password to unlock cells: abc
DHIS2Expert/Researcher/Evaluator | 121 | 100 | 12100 | Role 1: Copied from Detailed Budget Estimate subtotals
Project Manager/DHIS2 Implementer | 193 | 60 | 11580 | Role 2: Copied from Detailed Budget Estimate subtotals
Analyst/App Developer/Tester | 93 | 45 | 4185 | Role 3: Copied from Detailed Budget Estimate subtotals
Senior Escalation Point | 6 | 150 | 900 | Role 4: Copied from Detailed Budget Estimate subtotals
People Costs |  |  | 28765
Expenses |  |  | 1250 | Have you included travel costs? If not, state that budget does not include travel.
|  | Total | 30015 | Should be identical with TOTAL COST OF PROJECT | 30015
|  | Plus HST for consulting costs at 13% | 3739.45 | For Canadian projects only
|  | TOTAL PROJECT BUDGET | 33754.45
This budget worksheet may be copied or adapted for nonprofit use, with attribution to LogicalOutcomes